## Costs
Req Analysis |  |  |  |  | Personnel | €/h |  | Day Working Hours
| count | working days |  | Cost |  |  |  | 8
PM | 2 | 5 |  |  | developer junior | 10
Senior Developer | 2 |  |  |  | developer senior | 16.5
System Engineer | 1 |  |  |  | designers | 10
Junior Developer | 3 |  |  |  | system engineer | 12.5
Designer | 1 |  |  |  | P.M. | 16.5
|  |  |  | 4740 | technical | 8
Planning |  |  |  |  | Data Science Expert | 15
| count | working days
PM | 1 | 4
System Engineer | 2
1328
Database |  |  |  |  | Service |  | Monthly costs
| count | working days |  |  | Azure SQL server |  | 1938 |  | 23256
Senior Developer | 2 | 8
Junior Developer | 4
|  |  |  | 4672 | Total |  | 1938
Informer
| count | working days
Senior Developer | 4 | 15
Junior Developer | 6
Designer | 1
16320
Cultivation Manager
| count | working days
Senior Developer | 4 | 15
Junior Developer | 6
Designer | 2
17520
Cultivation Automizer
| count | working days
Senior | 8 | 15
Junior Developer | 6
Designer | 1
Data Scientist | 4
31440
Cultivation Supervisor
| count | working days
Senior Developer | 4 | 15
Junior Developer | 8
Designer | 1
18720
Testing
| count | working days
Technical | 3 | 5
960
Customer Approval
| count | working days
PM | 1 | 1
132
Installation
| count | working days
System Engineer | 1 | 1
Technical | 3
292
Staff Training
| count | working days
Technical | 5 | 5
1600
|  |  | Total Labor Cost | 97724
|  |  | Total | 99662

## Profit&Loss
Hydrome profit & loss
Sales Revenue | 276744
Cost of goods | 99662
Gross Profit | 177082
Fixed Costs
Accounting | 1000
Advertising | 450
Insurance | 1000
Miscellaneous | 200
Legal Expenses | 600
Licenses | 1000
Office supplies | 150
Postage and Printing | 300
R&D | 2000
Telephone | 400
Traning and Seminars | 1500
Utilities | 3000
Total Fixed Costs | 11600
EBIT | 165482
Interests | 2000
Earning after Interests | 163482
Taxes | 22%
EAT | 127515.96
Margin | 46.0772

## Gantt
Tasks | Start Date | Duration | End Date | Milestones
Start Project | 2020-06-01 | 1 | 2020-06-02 | Requirement Definition Milestone |  | Delivery Deadline
Requirement Analysis | 2020-06-01 | 6 | 2020-06-07 | 2020-06-07 | 0 | 2020-07-06 | 0
Planning | 2020-06-07 | 4 | 2020-06-11 | 2020-06-07 | 1 | 2020-07-06 | 1
Database | 2020-06-11 | 10 | 2020-06-21
SW Informer | 2020-06-11 | 21 | 2020-07-02 | Demo Milestone
SW Cultivation Manager | 2020-06-11 | 21 | 2020-07-02 | 2020-06-21 | 0
SW Cultivation Automizer | 2020-06-11 | 21 | 2020-07-02 | 2020-06-21 | 1
SW Cultivation Supervisor | 2020-06-11 | 21 | 2020-07-02
Testing | 2020-06-26 | 6 | 2020-07-02 | Development
Customer Approval | 2020-07-02 | 1 | 2020-07-03 | 2020-07-02 | 0
Installation | 2020-07-03 | 1 | 2020-07-04 | 2020-07-02 | 1
Staff Training | 2020-06-29 | 7 | 2020-07-06
End Project | 2020-07-05 | 1 | 2020-07-06 | Release Milestone
|  |  |  | 2020-07-04 | 0
|  |  |  | 2020-07-04 | 1
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]-[Duration, row above]
Start Date = [End Date, row above]
Milestones = [End Date]
Milestones = [Milestones, row above]