## Gantt
Tasks | Start Date | Duration | End Date | Milestones
Start Project | 2020-06-22 | 1 | 2020-06-23 | Design Phase Milestone |  | Second Demo |  | System Prototype Milestone
Design Document Writing | 2020-06-22 | 7 | 2020-06-29 | 2020-06-29 | 0 | 2020-08-17 | 0 | 2020-11-16 | 0
Architecture Definition | 2020-06-29 | 7 | 2020-07-06 | 2020-06-29 | 1 | 2020-08-17 | 1 | 2020-11-16 | 1
Dashboard Design Document | 2020-07-06 | 7 | 2020-07-13
Storage Setup | 2020-07-13 | 7 | 2020-07-20 | Architecture Definition Milestone |  | Third Demo |  | Test report and Deployment
SW Data Collection Suite | 2020-07-20 | 70 | 2020-09-28 | 2020-07-06 | 0 | 2020-09-14 | 0 | 2020-12-14 | 0
SW Data Analysis Suite | 2020-07-20 | 70 | 2020-09-28 | 2020-07-06 | 1 | 2020-09-14 | 1 | 2020-12-14 | 1
SW Social Science Suite | 2020-07-20 | 70 | 2020-09-28
Dashboard Design | 2020-09-19 | 30 | 2020-10-19 | Dashboard Design Proposal |  | Fourth Demo
Search Engine Implementation | 2020-10-02 | 30 | 2020-11-01 | 2020-07-13 | 0 | 2020-10-12 | 0
Testing | 2020-11-01 | 15 | 2020-11-16 | 2020-07-13 | 1 | 2020-10-12 | 1
Staff Training | 2020-11-16 | 20 | 2020-12-06
Client Test Phase | 2020-11-16 | 28 | 2020-12-14 | First Demo |  | Dashboard Design Milestone
End Project | 2020-12-13 | 1 | 2020-12-14 | 2020-07-20 | 0 | 2020-10-19 | 0
|  |  |  | 2020-07-20 | 1 | 2020-10-19 | 1
Formulas:
End Date = [Start Date]+[Duration]
Start Date = [End Date, row above]-[Duration, row above]
Start Date = [End Date, row above]
Milestones = [End Date]
Milestones = [Milestones, row above]

## Cost
Design Document | [5 empty] | Personnel | €/h |  | Day Working Hours
| count | working days |  | Cost |  |  |  |  | 8
PM | 3 | 5 |  |  |  | developer junior | 10
Senior Developer | 2 |  |  |  |  | developer senior | 16.5
System Engineer | 1 |  |  |  |  | designers | 10
Data Science Expert | 3 |  |  |  |  | system engineer | 12.5
Designer | 2 |  |  |  |  | P.M. | 16.5
|  |  |  | 6400 |  | technical | 8
Architecture Definition | [5 empty] | Data Science Expert | 15
| count | working days
PM | 2 | 5
System Engineer | 2
Senior Developer | 2
|  |  |  | 3640 |  | Service |  | Monthly costs
Dashboard Design Document | [5 empty] | Azure HDInsight + Database |  | 2200
| count | working days |  |  |  | Microsoft Dynamics 365 |  | 2300
PM | 2 | 5
Designer | 3 |  |  |  |  | Total |  | 4500
Senior Developer | 2
3840
Storage Setup
| count | working days
System Engineer | 2 | 5
Senior Developer | 2
2320
Data Collection Suite
| count | working days
Developer Senior | 3 | 50
Developer Junior | 5
Data Science Expert | 2
51800
Data Analysis Suite
| count | working days
Developer Senior | 3 | 50
Developer Junior | 5
Data Science Expert | 3
57800
Social Science Suite
| count | working days
Developer Senior | 2 | 50
Developer Junior | 2
Data Science Expert | 4
45200
Dashboard Design
| count | working days
Developer Senior | 1 | 20
Designer | 3
7440
Search Engine Implementation
| count | working days
Senior Developer | 1 | 20
Junior Developer | 3
7440
Testing
| count | working days
Technical | 5 | 10
3200
Staff Training
| count | working days
Technical | 3 | 15
2880
Client Testing Support
| count | working days
Technical | 2 | 21
2688
|  |  | Total Labor Cost | 149448
|  |  | Additional Features Cost |  | 45200
|  |  | Total | 171948
|  |  | Total with additional features |  | 217148

## Profit&Loss
IR2 profit & loss
Sales Revenue | 315000
Cost of goods | 217148
Gross Profit | 97852
Fixed Costs
Accounting | 2500
Advertising | 1125
Insurance | 2500
Miscellaneous | 500
Legal Expenses | 1500
Licenses | 2500
Office supplies | 375
Postage and Printing | 750
R&D | 4500
Telephone | 1000
Traning and Seminars | 3750
Utilities | 7500
Total Fixed Costs | 28500
EBIT | 69352
Interests | 5000
Earning after Interests | 64352
Taxes | 22%
EAT | 50194.56
Margin | 15.9348